RESTORA POS

Restaurant Management Software

Implementation Plan & Infrastructure Setup Guide

| Total Duration | 39 Weeks (10 Months) |
| --- | --- |
| Team Size | 2–3 Full-Stack Developers |
| Phases | 8 Phases |
| Version | 1.0 — April 2025 |

# 1. Infrastructure & Server Setup

This section details every server, service, and third-party account you need to set up before a single line of code is written. These are the answers to your question: 'What do I need?'

## 1.1 Server Requirements

| Component | Recommended | Minimum | Cost (USD/mo) |
| --- | --- | --- | --- |
| Application Server | DigitalOcean Droplet 4 vCPU / 8GB RAM / 160GB SSD | 2 vCPU / 4GB RAM / 80GB SSD | ~$48 |
| Database Server | PostgreSQL 15 — Managed DB (DigitalOcean) 2 vCPU / 4GB RAM | Self-hosted on app server (dev only) | ~$50 |
| Redis Cache | Redis 7 — Managed (DigitalOcean) 1GB RAM | Self-hosted on app server (dev only) | ~$15 |
| File Storage | Cloudflare R2 (S3-compatible, free egress) 10GB | AWS S3 (pay-per-use) | ~$0–5 |
| CDN | Cloudflare Free (for static assets, SSL, DDoS protection) | None needed initially | $0 |
| Domain | 1 primary domain + wildcard subdomain (e.g. *.restora.app) | 1 primary domain | ~$15/yr |
| SSL Certificate | Auto-managed via Cloudflare or Let's Encrypt + Certbot | Let's Encrypt (free) | $0 |
| Email | SendGrid Free Tier (100 emails/day) for transactional email | None initially | $0 |
| Monitoring | Better Uptime (free) for uptime monitoring | None initially | $0 |

## 1.2 Domain & Subdomain Structure

| Subdomain | Purpose | Environment |
| --- | --- | --- |
| restora.app (or your domain) | QR Order PWA — customer-facing | Production |
| app.restora.app | Admin Panel + POS — staff-facing | Production |
| api.restora.app | NestJS API Server | Production |
| kds.restora.app | Kitchen Display System | Production |
| staging.restora.app | Full staging environment | Staging |
| api-staging.restora.app | Staging API | Staging |

## 1.3 Third-Party Accounts to Create

Create all of these before starting development:

- GitHub Organization — private repositories for all code

- DigitalOcean — main cloud hosting (or AWS EC2 alternative)

- Cloudflare — DNS management, CDN, free SSL, R2 file storage

- SendGrid — transactional email (order confirmations, staff notifications)

- Sentry — real-time error tracking for frontend and backend

- GitHub Actions — CI/CD pipeline (included with GitHub)

- Docker Hub — container image registry (free tier sufficient)

- Better Uptime or UptimeRobot — server uptime monitoring

- bKash/Nagad Developer Portal — MFS payment reference (Phase 2)

- Twilio or Sparrow SMS — SMS notifications for BD (Phase 2)

## 1.4 Local Development Setup

Each developer needs the following installed on their machine:

- Node.js 20 LTS — via nvm (Node Version Manager)

- PostgreSQL 15 — via Homebrew (Mac), WSL2 (Windows), or Docker

- Redis 7 — via Homebrew or Docker

- Docker Desktop — for running the full stack locally in containers

- Git — with SSH key configured for GitHub

- VS Code — with ESLint, Prettier, Prisma, and GitLens extensions

- TablePlus or DBeaver — PostgreSQL GUI client

- Insomnia or Postman — API testing client

- pnpm — faster npm alternative (npm install -g pnpm)

# 2. Repository & Project Structure

## 2.1 Monorepo Layout

All code lives in a single GitHub monorepo managed with pnpm workspaces:

| Path | Contents | Framework |
| --- | --- | --- |
| apps/api/ | NestJS REST API + WebSocket server | NestJS + Prisma |
| apps/pos/ | POS terminal SPA | React 18 + Vite |
| apps/admin/ | Admin panel SPA | React 18 + Vite |
| apps/kds/ | Kitchen Display System | React 18 + Vite |
| apps/qr-order/ | QR Order PWA (mobile-first) | React 18 + Vite + PWA |
| packages/ui/ | Shared component library (design system) | React + TailwindCSS |
| packages/types/ | Shared TypeScript types and interfaces | TypeScript |
| packages/utils/ | Shared utility functions | TypeScript |
| packages/config/ | Shared config: ESLint, Prettier, TS config | JSON + JS |
| infra/ | Docker Compose, Nginx config, CI/CD scripts | YAML + Shell |
| prisma/ | Database schema, migrations, seed data | Prisma Schema |
| docs/ | API documentation, architecture diagrams | Markdown |

## 2.2 Environment Variables (per app)

Create .env.example files for every app. Never commit .env files. Use GitHub Secrets for CI/CD.

| Variable | Description | Required For |
| --- | --- | --- |
| DATABASE_URL | PostgreSQL connection string | API |
| REDIS_URL | Redis connection string | API |
| JWT_SECRET | JWT signing secret (minimum 64 chars, random) | API |
| JWT_REFRESH_SECRET | JWT refresh token secret (different from above) | API |
| CLOUDFLARE_R2_ENDPOINT | R2 S3-compatible endpoint URL | API |
| CLOUDFLARE_R2_ACCESS_KEY | R2 access key ID | API |
| CLOUDFLARE_R2_SECRET_KEY | R2 secret access key | API |
| CLOUDFLARE_R2_BUCKET | R2 bucket name | API |
| SENDGRID_API_KEY | SendGrid API key for transactional email | API |
| SENTRY_DSN | Sentry project DSN for error tracking | API + Frontends |
| VITE_API_URL | Backend API base URL (for React apps) | All frontends |
| VITE_WS_URL | WebSocket server URL (for React apps) | POS, KDS, QR |
| VITE_SENTRY_DSN | Sentry DSN for frontend error tracking | All frontends |

# 3. Development Phase Roadmap

The 39-week development plan is divided into 8 sequential phases. Each phase delivers a testable, deployable increment of the system.

| Phase | Name | Duration | Start Week | End Week | Priority |
| --- | --- | --- | --- | --- | --- |
| P1 | Core POS & Orders | 8 weeks | Week 1 | Week 8 | Ready to Build |
| P2 | Inventory & Recipe Engine | 6 weeks | Week 9 | Week 14 | Foundation |
| P3 | Purchasing & Suppliers | 4 weeks | Week 15 | Week 18 | Foundation |
| P4 | QR Self-Order System | 5 weeks | Week 19 | Week 23 | Advanced |
| P5 | Finance & Reporting | 5 weeks | Week 24 | Week 28 | Advanced |
| P6 | Staff & Payroll | 4 weeks | Week 29 | Week 32 | Advanced |
| P7 | KDS & Waste Management | 3 weeks | Week 33 | Week 35 | Advanced |
| P8 | Polish, Scale & Hardening | 4 weeks | Week 36 | Week 39 | Foundation |

# 4. Phase 1 — Core POS (Weeks 1–8)

This is the most critical phase. At the end of Week 8, you must have a working POS that can take orders, print kitchen tickets, and accept payment. Everything else builds on this.

## 4.1 Week-by-Week Breakdown

| Week | Backend Tasks | Frontend Tasks |
| --- | --- | --- |
| Week 1 | Monorepo setup, Prisma schema (users, branches, roles), Auth module (JWT + refresh) | Vite + React + TailwindCSS setup, design system tokens, routing structure |
| Week 2 | Menu module (categories, items, variants), Inventory item master (basic) | Admin shell: Login page, dashboard shell, menu management CRUD screens |
| Week 3 | POS module: order creation, order types (Dine-In/Takeaway/Delivery), order status lifecycle | POS shell: category rail, menu grid, cart panel layout |
| Week 4 | Table management (floor plan data model), order-table linking, cover count | POS: floor plan visual grid, table state colors, order creation flow |
| Week 5 | Kitchen Ticket print job queue, Print service microservice, printer routing by category | POS: checkout flow UI, payment method selection UI, receipt preview |
| Week 6 | Payment module (cash, MFS, card, split), payment validation, order close logic | POS: payment processing screens, split payment UI, change calculator |
| Week 7 | Order void flow (Manager approval), void reason logging, stock reversal hook (stub) | POS: void flow with PIN entry, manager approval UI, void history |
| Week 8 | E2E testing: full order lifecycle from create to payment, load testing 50 terminals | Integration testing, bug fixes, staging deployment, user acceptance testing |

## 4.2 Phase 1 Deliverables — Definition of Done

- Staff can log in with role-specific access (Owner, Manager, Cashier)

- All three order types creatable (Dine-In, Takeaway, Delivery)

- Table floor plan rendered, table states update in real-time

- Kitchen Ticket auto-prints on order submission to configured printer

- Cash, MFS, Card, and Split payments accepted and recorded

- Order void requires Manager PIN and records reason

- Full order close records to accounts and generates receipt

- System handles 50 concurrent POS sessions without degradation

# 5. Phase 2 — Inventory & Recipe Engine (Weeks 9–14)

The Recipe Engine is the most technically complex module. It must be accurate to 4 decimal places and handle unit conversions, FIFO batch deduction, and cascading pre-ready stock.

## 5.1 Technical Implementation Notes

- All quantities stored in base storage unit with NUMERIC(14,4) precision in PostgreSQL

- Unit conversion table seeded at setup: 1kg = 1000g, 1L = 1000ml, 1 tbsp = 15ml, etc.

- Stock deduction triggered as a database transaction on Kitchen Ticket insert — atomic or rollback

- Pre-Ready FIFO: query batches ORDER BY making_date ASC, deduct from oldest non-expired first

- Recipe costing recalculated nightly via BullMQ scheduled job (not on every query)

- Stock ledger is append-only — never update or delete rows, only insert new entries

## 5.2 Week Breakdown

| Week | Focus Area | Key Deliverables |
| --- | --- | --- |
| Week 9 | Inventory Item Master | Full CRUD, SKU generation, category system, storage/purchase units, reorder levels |
| Week 10 | Stock Ledger Engine | Ledger schema, all transaction types, stock balance view, adjustment with reason |
| Week 11 | Recipe Management | Recipe CRUD, unit conversion logic, recipe cost calculation, recipe line validation |
| Week 12 | Stock Deduction on KT | Recipe engine hook on KT print, atomic transaction, error handling if stock insufficient |
| Week 13 | Pre-Ready Food System | Pre-Ready item master, batch production flow, KPT generation, FIFO deduction |
| Week 14 | Expiry Tracking + Reports | Batch expiry dates, warning/critical alerts, current stock report, monthly stock report |

# 6. Phases 3–8 — Summary Plan

## Phase 3 — Purchasing & Suppliers (Weeks 15–18)

- Week 15: Supplier CRUD, supplier-item mapping, preferred supplier flags

- Week 16: Shopping list auto-generation from low stock, manual editing, Draft PO creation

- Week 17: GRN receiving flow — quantity entry, price entry, batch date setting, stock update on submit

- Week 18: Supplier invoicing, partial/full payment recording, supplier payment history, due tracking

## Phase 4 — QR Self-Order System (Weeks 19–23)

- Week 19: QR Order PWA setup (Vite PWA), QR code generation per table, mobile menu layout

- Week 20: Customer order creation flow, cart management, order submission to POS

- Week 21: Real-time order status via WebSocket, customer-side status page, prep time countdown

- Week 22: Customer cancel (pre-accept), problem reporting, add-to-order, bill request feature

- Week 23: Multi-language (EN/BN), upsell suggestions, allergen display, offline handling

## Phase 5 — Finance & Reporting (Weeks 24–28)

- Week 24: Account management (Cash, Bank, MFS, Card), manual transfers, balance tracking

- Week 25: Expense management, categories, recurring expenses, daily/monthly expense views

- Week 26: Daily and monthly sales reports, date-range report, payment method breakdown

- Week 27: Sales vs Food Cost report using recipe consumption data, GP% calculation

- Week 28: Monthly P&L auto-generation, PDF export, Excel export (using ExcelJS)

## Phase 6 — Staff & Payroll (Weeks 29–32)

- Week 29: Employee profiles, document storage, employment status management

- Week 30: Attendance tracking via POS PIN check-in, attendance reports, late flagging

- Week 31: Leave types, balance, application flow, manager approval, payroll integration

- Week 32: Monthly payroll run, advance management, salary slip PDF generation

## Phase 7 — KDS & Waste Management (Weeks 33–35)

- Week 33: KDS full-screen app, live order queue via WebSocket, color-coded aging, item ready marking

- Week 34: Waste entry form, reason codes, manager approval threshold, stock deduction on waste

- Week 35: Full notification system — low stock, expiry, QR order alerts, void approvals

## Phase 8 — Polish, Scale & Hardening (Weeks 36–39)

- Week 36: PWA offline mode for POS — local IndexedDB queue, sync on reconnect

- Week 37: Multi-branch architecture validation, RLS testing, branch-level config isolation

- Week 38: Performance optimization — database query analysis, Redis cache tuning, bundle size

- Week 39: Security audit, penetration testing basics, audit log review, final UAT with real restaurant

# 7. CI/CD Pipeline Setup

GitHub Actions handles all automated builds, tests, and deployments.

## 7.1 Pipeline Stages

| Stage | Trigger | Actions | Target |
| --- | --- | --- | --- |
| Lint & Type Check | Every push to any branch | ESLint, TypeScript compiler check | — |
| Unit Tests | Every push to any branch | Vitest (frontend), Jest (backend) | — |
| Build | Every push to main or staging | Build all apps, Docker image build | — |
| Integration Tests | Push to staging branch | Playwright E2E tests against staging | Staging |
| Deploy to Staging | Push to staging branch (after tests pass) | Docker push + SSH deploy to staging server | Staging |
| Deploy to Production | Manual trigger after staging approval | Docker push + SSH deploy to production server | Production |
| DB Migration | After deploy (auto) | Prisma migrate deploy on server | Both envs |

## 7.2 GitHub Actions Secrets to Configure

- PROD_SERVER_HOST — production server IP address

- PROD_SERVER_USER — SSH user (typically: deploy or ubuntu)

- PROD_SSH_PRIVATE_KEY — SSH private key for passwordless deploy

- STAGING_SERVER_HOST — staging server IP

- STAGING_SSH_PRIVATE_KEY — staging SSH key

- DOCKER_USERNAME — Docker Hub username

- DOCKER_PASSWORD — Docker Hub access token

- DATABASE_URL — production DB connection string

- JWT_SECRET — 64+ character random string

- SENTRY_AUTH_TOKEN — for source map uploads to Sentry

# 8. Team Structure & Responsibilities

| Role | Count | Primary Responsibilities | Required Skills |
| --- | --- | --- | --- |
| Lead Full-Stack Developer | 1 | Architecture, API design, database schema, code review, DevOps | NestJS, PostgreSQL, Docker, React |
| Full-Stack Developer | 1–2 | Feature development across frontend and backend, testing | React, NestJS, TypeScript |
| UI/UX Designer (Part-time) | 1 | Figma designs for each screen, design system maintenance, UX reviews | Figma, design systems |
| QA Tester (Part-time) | 1 | Manual testing, writing Playwright E2E tests, UAT coordination | Playwright, testing methodologies |
| Restaurant Domain Expert | 1 (client) | Feature validation, UAT, real-world workflow verification | Restaurant operations knowledge |

## 8.1 Weekly Ceremonies

- Monday Sprint Planning (1hr) — select weekly tasks from backlog, assign owners

- Wednesday Stand-up (15min) — progress, blockers, help needed

- Friday Demo (30min) — demo working features to client/stakeholder, collect feedback

- End of Phase Review — feature walkthrough, UAT session with real restaurant staff

# 9. Complete Technology Stack

## 9.1 Backend Stack

| Package | Version | Purpose |
| --- | --- | --- |
| @nestjs/core | ^10 | Core application framework |
| @nestjs/jwt | ^10 | JWT authentication |
| @nestjs/websockets + socket.io | ^10 + ^4 | Real-time WebSocket events |
| prisma + @prisma/client | ^5 | ORM and database access |
| ioredis | ^5 | Redis client for cache and pub/sub |
| bullmq | ^5 | Background job queue (reports, payroll, alerts) |
| bcrypt | ^5 | Password hashing |
| class-validator + class-transformer | ^0.14 | DTO validation and transformation |
| @nestjs/swagger | ^7 | OpenAPI documentation generation |
| winston | ^3 | Application logging |
| @aws-sdk/client-s3 | ^3 | Cloudflare R2 / S3 file uploads |
| @nestjs/schedule | ^4 | Cron jobs for nightly stock revaluation |
| exceljs | ^4 | Excel report generation |
| puppeteer or pdfmake | latest | PDF generation for salary slips, invoices |

## 9.2 Frontend Stack

| Package | Version | Purpose |
| --- | --- | --- |
| react + react-dom | ^18 | Core UI framework |
| vite | ^5 | Build tool and dev server |
| @vitejs/plugin-react | ^4 | React fast refresh |
| vite-plugin-pwa | ^0.19 | PWA support for QR Order app |
| tailwindcss | ^3 | Utility-first CSS framework |
| @tanstack/react-query | ^5 | Server state management, caching |
| zustand | ^4 | Client UI state (cart, modals, POS state) |
| react-hook-form + zod | latest | Form state and validation |
| @tanstack/react-table | ^8 | Data tables with sorting and filtering |
| recharts | ^2 | Chart components for dashboards |
| socket.io-client | ^4 | WebSocket connection |
| react-router-dom | ^6 | Client-side routing |
| date-fns | ^3 | Date manipulation and formatting |
| react-to-print | latest | Browser-based print for receipts/KT |
| lucide-react | latest | Icon library |
| @sentry/react | latest | Frontend error tracking |

# 10. Database Setup & Schema Bootstrap

## 10.1 PostgreSQL Configuration

- Version: PostgreSQL 15 (minimum 14)

- Create three databases: restora_production, restora_staging, restora_dev

- Create a dedicated application user with limited privileges (not superuser)

- Enable pg_stat_statements extension for query performance monitoring

- Set max_connections = 100 on managed instance; use PgBouncer for connection pooling

- Automated daily backup to Cloudflare R2 via pg_dump cron job, 30-day retention

## 10.2 Critical Prisma Schema Decisions

- All monetary values: Decimal (precision 14, scale 2) stored in smallest unit (paisa for BDT)

- All quantities: Decimal (precision 14, scale 4) to handle sub-ml measurements

- Multi-tenancy: Every table includes branch_id with Row-Level Security policies

- Soft deletes: All major entities have deleted_at DateTime? field; never hard delete

- Audit trail: All write operations append to audit_log table with before/after JSON

- Timestamps: created_at and updated_at on all tables, auto-managed by Prisma

## 10.3 Redis Configuration

- Database 0: Session tokens and JWT blacklist

- Database 1: Server-sent data cache (menu, categories — 15min TTL)

- Database 2: BullMQ job queues (reports, payroll, alerts)

- Database 3: WebSocket room data (active orders per branch)

- Set maxmemory-policy = allkeys-lru (evict least-recently-used on memory pressure)

# 11. Security Checklist

## 11.1 Pre-Launch Security Requirements

| Security Item | Implementation | Priority |
| --- | --- | --- |
| HTTPS everywhere | Cloudflare SSL + enforce HTTPS redirect in Nginx | Critical |
| JWT rotation | Access token: 15min TTL. Refresh token: 30 days, rotated on use | Critical |
| Password hashing | bcrypt with cost factor 12 | Critical |
| Rate limiting | Auth endpoints: 5 req/15min per IP. API: 100 req/min per user | Critical |
| SQL injection prevention | Prisma parameterized queries only — never string interpolation | Critical |
| XSS prevention | React inherently escapes; CSP headers via Nginx; sanitize rich text | High |
| CORS restriction | Allow only configured frontend origins; reject all others | High |
| RLS enforcement | PostgreSQL RLS policies on all branch-scoped tables | High |
| File upload security | Validate MIME type server-side; max 5MB; store in R2, not server disk | High |
| Audit logging | All void, delete, payment, config changes logged with user + diff | High |
| Secrets management | All secrets in environment variables; never in code or git | Critical |
| Dependency scanning | GitHub Dependabot enabled; npm audit on every CI run | Medium |

# 12. Testing Strategy

| Test Type | Tool | Coverage Target | When |
| --- | --- | --- | --- |
| Unit Tests — Backend | Jest + NestJS testing utilities | 80% of service methods | Every commit |
| Unit Tests — Frontend | Vitest + React Testing Library | Key components and hooks | Every commit |
| Integration Tests | Jest + Supertest (API tests) | All API endpoints | Every commit |
| E2E Tests — POS | Playwright | Core POS flows: order, payment, void | Staging deploy |
| E2E Tests — Admin | Playwright | Menu, inventory, reports | Staging deploy |
| Performance Tests | k6 (load testing) | 50 concurrent POS sessions | Pre-production |
| Security Scan | npm audit + OWASP ZAP | All critical endpoints | Pre-launch |
| UAT | Real restaurant staff | Full workflow walkthrough | End of each phase |

# 13. Monitoring & Observability

## 13.1 Monitoring Stack

| Tool | Purpose | What It Monitors |
| --- | --- | --- |
| Sentry | Error tracking | JavaScript exceptions, unhandled promise rejections, API 5xx errors |
| Better Uptime | Uptime monitoring | API health endpoint, frontend URLs — alerts if down |
| Prometheus + Grafana | Metrics dashboard | API response times, request rates, queue depths, DB connections |
| PostgreSQL slow query log | DB performance | Queries exceeding 100ms — logged to file for analysis |
| Redis Monitor | Cache health | Cache hit rate, memory usage, eviction count |
| Nginx access logs | Traffic analysis | Request volume, error rates, IP distribution |
| Docker stats | Container health | CPU, memory usage per container — alert on >80% |

## 13.2 Alert Thresholds

- API response time p95 > 500ms: send Slack/email alert

- Any 5xx error spike > 5 per minute: immediate alert

- Server CPU > 80% sustained for 5 minutes: alert

- Database connections > 80 of max: alert

- Redis memory > 80%: alert

- Disk usage > 75%: alert (for database and log volumes)

# 14. Summary — What You Need to Get Started

Below is the exact checklist for Day 1. Complete all items before writing code:

| Task | Who | Time Needed |
| --- | --- | --- |
| Create GitHub Organization and private monorepo | Lead Dev | 30 min |
| Create DigitalOcean account, create 2 Droplets (prod + staging) | Lead Dev | 1 hour |
| Point domain to Cloudflare DNS, configure subdomains | Lead Dev | 1 hour |
| Create Cloudflare R2 bucket for file storage | Lead Dev | 20 min |
| Create SendGrid account, verify sending domain | Lead Dev | 30 min |
| Create Sentry organization, add 2 projects (api, frontend) | Lead Dev | 20 min |
| Create Docker Hub account, set up GitHub Actions secrets | Lead Dev | 1 hour |
| Configure SSH key-based access to both servers | Lead Dev | 30 min |
| Set up managed PostgreSQL and Redis on DigitalOcean | Lead Dev | 1 hour |
| Install Node 20, pnpm, Docker on all developer machines | All Devs | 1 hour |
| Bootstrap monorepo with pnpm workspaces, base configs | Lead Dev | 2 hours |
| Write and run Prisma schema with initial migration | Lead Dev | 3 hours |
| Deploy skeleton NestJS API to staging with health endpoint | Lead Dev | 2 hours |
| Deploy skeleton React app (pos + admin) to staging | Lead Dev | 2 hours |
| Confirm CI/CD pipeline runs end-to-end | Lead Dev | 2 hours |
| Kick off Phase 1 Sprint Planning with full team | All | 1 hour |

End of Document

Restora POS — Implementation Plan v1.0  |  April 2025  |  Confidential